## Risikomanagement
ID | Datum | Gruppe | Risiko | Beschreibung | Mögliche Maßnamen | Quelle | resp. | Due Date |  |  |  |  | Projektauswirkung | Eintrittswahrscheinlichkeit | Status | Anmerkung
[9 empty] | Zeit | Budget | Qualität | Ressourcen
[9 empty] | 1 | 1 | 2 | 1
RS001 | 2015-04-01 | group3 | communication matrix may contain errors | CAN-communication fails. It would have to be corrected within the next work package | check data early | Manuel | Manuel | 2015-04-27 | 50% | 0% | 0% | 0% | 10% | 20% | open
RS002 | 2015-04-18 | group 3 | simulink battery-model may not match reality | due to wrong parameter or done simplification, the applied model of a battery may missmatch a real battery. The developement of BMS and MiL test may not be precise then. | Simulate behaviour and compare to real battery or expected behaviour. | Manuel | team | 2015-04-20 | 20% | 0% | 50% | 0% | 24% | 20% | open
[5 empty] | Input / output signals can lead to a deviation form | Ingmar | team | 2015-04-24 | 10% | 0% | 30% | 0% | 14% |  | open
[13 empty] | 0% |  | open
[13 empty] | 0% |  | open
[13 empty] | 0% |  | open
[13 empty] | 0% |  | open
[13 empty] | 0% |  | open
[13 empty] | 0% |  | open
[13 empty] | 0% |  | open
[13 empty] | 0% |  | open
[13 empty] | 0% |  | open
[13 empty] | 0% |  | open